## Sheet1
EVENT TIMELINE ¦ [Event Name]
[event date]
[event location]
Activity | Responsibility | Date
Three Months to Eight Weeks Ahead (Planning duration depends on the scope of event)
Contact Gloria Chu, Director of Ceremonies and Events for an event consultation (if applicable).
Review the SFU Event Planning Toolkit.
Draft an Event Brief (using the template provided by Ceremonies and Events) outlining the goals and objectives of the event.
Schedule an Event Strategy meeting with event leads to review the Event Brief and begin the event planning process.
Select a few dates and times for the event and confirm a date with the President’s Office and/or key SFU staff.
Book a venue.
Finalize the Event Brief and circulate to event leads and internal stakeholders.
Begin compiling an invitation list.
Design invitations.
Eight Weeks Ahead
Draft program schedule.
Confirm all speakers.
Finalize mail list; circulate to event leads and internal stakeholders to review.
Finalize invitations and obtain approvals.
Prepare work orders: A/V, staging, equipment, photographer, refreshments, décor, parking, facilities management, security, etc.
Determine marketing/public relations plan (if a public event).
Consult with University Communications, MECS, IT Services, Security and Parking about event.
Six to Four Weeks Ahead
Send out invitations (print or evite).
Draft speaking notes for key SFU speakers (in consultation with the President’s Office if the President will be speaking).
Draft print program (if you plan to distribute at event).
Make arrangements for staffing the event.
Three Weeks Ahead
Circulate a report listing the names and the number of guests confirmed to event leads/internal stakeholders (if you are collecting registrations).
Purchase gifts and arrange honourariums for speakers (if applicable).
Print program is approved for printing.
Confirm details and program schedule with all speakers.
Two Weeks Ahead
Ensure all work orders/arrangements for equipment, staging, décor, refreshments, parking, security, etc. are confirmed.
Practice the event by “walking through” all the steps of the Program Schedule to ensure all the details have been arranged. (Tip: Visualize yourself as guest arriving to the event – parking arrangements, directional signs, welcome, reception, location of event).
Create an event day timeline of activities to use as a checklist on the day of the event (Detailed Program Schedule).
Brief staff, volunteers, speakers, President (if applicable) about event. Ensure that you have assigned someone to meet dignitaries as they arrive onsite and someone to greet and brief suppliers (e.g. photographer, catering, A/V).
One Week Ahead
Final draft of the Book of Words and Event Briefing are complete. Circulate to event leads and speakers for review and input.
Ceremonies and Events will review the Book of Words and then pass it onto President Petter (if applicable).
Ensure that speakers, AV staff, caterers, event staff, volunteers and all key participants have an updated event program schedule.
Three Days Before
Confirm registration numbers and dietary restrictions with catering.
Confirm the event site will be ready for set-up on the day of the event (e.g. cleaning arranged).
Re-confirm arrival of all equipment, staging, décor and other suppliers.
Review guest registration list (Expected Attendance Report) and note VIP guests who need to be acknowledged in the Book of Words.
Pack event supplies and arrange for transportation to the venue.
Day of Event
Create a list of contact numbers of speakers, suppliers and other key contacts.
Arrive early to ensure the room is set-up correctly.
Check that A/V equipment is in place. Test all AV and conduct a sound check.
Set-up name tags and registration table.
Ensure that the event day timeline of activities is on schedule:
· confirm timing with banquet captain
· have all speakers arrived?
· have all VIPs arrived?
· has the photographer arrived?
· have performers arrived?
Brief speakers onsite. Review program and complete sound check.
Following Event
Send thank you notes and photos to sponsors, speakers, volunteers, attendees, etc.
Schedule an event debrief with event leads.
Evaluate event success. Were all goals and objectives achieved? Administer event survey (optional).