## With Milestones
PROJECT TITLE
PI Name
Project Time Period
|  | Columns C-H populated with sample dat to show how the table works | [6 empty] | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4
TASK NO. | TASK DESCRIPTION | PLANNED Q START | PLANNED Q END | PLANNED DURATION | ACTUAL Q START | ACTUAL Q END | ACTUAL DURATION | % COMPLETE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Activity Description, i.e. Literature Review | 1 | 4 | 4 | 2 | 7 | 6
1.1 | Sub-activity description | 1 | 2 | 2 | 4 | 5 | 2
1.2 | Sub-activity description | 1 | 3 | 3 | 4 | 6 | 3
1.3 | Sub-activity description | 2 | 3 | 2 | 2 | 4 | 3
1.4 | Sub-activity description | 3 | 4 | 2 | 4 | 5 | 2
1.5 | Sub-activity description | 3 | 4 | 2 | 6 | 7 | 2
2 | Activity Description, i.e. Data Collection | 3 | 8 | 6 | 0 | 0 | 1
2.1 | Sub-activity description | 3 | 4 | 2 |  |  | 1
2.2 | Sub-activity description | 3 | 6 | 4 |  |  | 1
2.3 | Sub-activity description | 5 | 7 | 3 |  |  | 1
2.4 | Sub-activity description | 6 | 7 | 2 |  |  | 1
2.5 | Sub-activity description | 7 | 8 | 2 |  |  | 1
3 | Activity Description, i.e. Data Analysis | 8 | 14 | 7 | 0 | 0 | 1
3.1 | Sub-activity description | 8 | 10 | 3 |  |  | 1
3.2 | Sub-activity description | 8 | 10 | 3 |  |  | 1
3.3 | Sub-activity description | 9 | 12 | 4 |  |  | 1
3.4 | Sub-activity description | 11 | 14 | 4 |  |  | 1
3.5 | Sub-activity description | 13 | 14 | 2 |  |  | 1
4 | Activity Description, i.e. Conclusions Compilation | 15 | 16 | 2 | 0 | 0 | 1
4.1 | Sub-activity description | 15 | 15 | 1 |  |  | 1
4.2 | Sub-activity description | 15 | 15 | 1 |  |  | 1
4.3 | Sub-activity description | 15 | 16 | 2 |  |  | 1
4.4 | Sub-activity description | 15 | 16 | 2 |  |  | 1
4.5 | Sub-activity description | 16 | 16 | 1 |  |  | 1
Legend for Duration Bars
Any color | Planned Duration
Actual Duration
[9 empty] | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q16
Milestone: Description
Deliverable: Description
Milestone: Description
Milestone: Description
Deliverable: Description
Milestone 5: Description
Deliverable: Description

## Instructions
Field | Instructions
Project Title, PI Name, and Project Time Period | Populate manually
Task No. | Populate manually in numerical order
Task Description | Populate manually
Planned Q Start, Planned Q End, Actual Q Start, Actual Q End for Main Activity Rows | Will populate automatically
Planned Q Start, Planned Q End, Actual Q Start, Actual Q End for sub-activities | Populate manually
Planned Duration, Actual Duration | Will populate automatically. Note that if the start and end date fields are blank, then the duration will just show as 1.
% Complete | Populate manually. Projects that are 100% complete will automatically highlight the % complete cell in red.
Colored Bars depicting start and end dates | Will populate automatically
Milestones | Populate manually
Notes
About Adding Rows | It will be easiest to add rows before the last sub-activity row in a section to ensure it picks up the proper formatting.
About Adding Sections | If a new section is needed, it will be easiest to copy an existing section and then change the color of the conditional formatting.
About Conditional Formatting | Sample conditional formatting formula for highlighting rows: =AND(J$5>=$F19, J$5<=$G19). Where J$5 represents the cell with the header label of the first quarter of the project. $F19 represents the start date for the first sub-activity row. $G19 represents the end date of the first sub-activity row.