## With Milestones
NSERC CREATE - full application development
PI Name
July -Sep 2020
[9 empty] | July |  |  | August |  |  |  | September
TASK NO. | TASK DESCRIPTION | ASSIGNED TO | START | END | DURATION | ACTUAL START | ACTUAL END | % COMPLETE | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10
1 | Planning Stage |  | W1 | W2 | bar: July W1 to July W2
1.1 | Strategic Planning Meeting led by ISA | ISA | W1 | W1 | bar: July W1
1.2 | Proposal Development Meeting with project team | PI | W2 | W2 | bar: July W2
2 | Development |  | W2 | W5 | bar: July W2 to August W5
2.1 | Confirm support & commitment of faculty(ies) and department(s) | RGF/PI | W2 | W3 | bar: July W2 to July W3
2.2 | Confirm commitments/contributions of external partners/supporters | RGF/PI | W2 | W3 | bar: July W2 to July W3
2.3 | Prepare/update Form 100/CCV/CVs and obtain signed T&C forms | PI/co-apps | W2 | W4 | bar: July W2 to August W4
2.4 | Obtain description of role of co-apps participating in active CREATEs | RGF/PI | W3 | W4 | bar: July W3 to August W4
2.5 | Solicit letters of support from collaborators | RGF/PI | W3 | W4 | bar: July W3 to August W4
2.6 | Compile co-applicant metrics (# of HQP, pubs, etc.) | RGF/PI | W5 | W5 | bar: August W5
2.7 | Draft Form 102, application for grant | PI | W2 | W5 | bar: July W2 to August W5
3 | Review and revision |  | W6 | W9 | bar: August W6 to September W9
3.1 | Internal/peer review - submit draft Form 102 to ISA by Aug 19 | ISA | W6 | W6 | bar: August W6
3.2 | Review feedback to PI | ISA | W7 | W7 | bar: August W7
3.3 | Revisions | PI | W7 | W8 | bar: August W7 to September W8
3.4 | Revise letters of support from collaborators | RGF/PI | W7 | W8 | bar: August W7 to September W8
3.5 | Final review if desired | ISA | W8 | W8 | bar: September W8
3.6 | Final edits | PI | W9 | W9 | bar: September W9
3.7 | Provide 'Summary of Training Program' component | ISA | W9 | W9 | bar: September W9
3.8 | Provide institutional support letter | ISA | W9 | W9 | bar: September W9
4 | Submission |  | W10 | W10 | bar: September W10
4.1 | Complete SFU sig sheet | PI | W10 | W10 | bar: September W10
4.2 | All documents submitted on NSERC online system | PI | W10 | W10 | bar: September W10
4.3 | ORS compliance check | ORS | W10 | W10 | bar: September W10
4.4 | Obtain signatures from authorized officer of each co-app's org | ORS | W10 | W10 | bar: September W10
4.5 | Submission to NSERC | ORS | W10 | W10 | bar: September W10
[9 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10
Review feedback to PI
Submission to NSERC
Form 102 draft to ISA for review
Submission to ORS